## USB002
AGRESSO TEST SCRIPT |  |  | Test result: |  | Date: | REF.NO: | USB002
AUTHOR: |  | Mike Smith | TEST: | Clash reinstatements journal
SCRIPT VERSION: |  | 1 | WORKSTREAM: | Syndicate / BIDAC
|  |  | TEST ROLE: | AG-GLREPORT
TEST DATE: |  |  | CLIENT: | SA and SB
TESTER: |  |  | SOFTWARE: | Desktop
PREREQUISITES: |  | A copy of the Excel template used to load clash reinstatements
Pre-Requisite scripts |  | (Link in 'Report' tab in this workbook)
Summary of test to be made: - Create the Agresso format data file - Validate the upload file - Upload the data - GL Account Review to vouch posting
STEP | DESCRIPTION |  | EXPECTED RESULT |  | ACTUAL RESULT | Pass/Fail | Defect ID
1 | Open a copy of the 'Clash reinstatements journal' spreadsheet. A link can be found in the 'Report' tab of this workbook.
2 | Navigate to the 'Journal' tab.
3 | Change the server used in cell B2 to the Milestone 7 testing server from the Live (ukprap071) server.
4 | - Change the 'period' parameter in cell C10 to the current accounting period in Agresso. - Change all of the rows in the 'trans_date' column (column M) to the last day of the current accounting period in Agresso. E.g. if the current accounting period is 202105, change this cell to 31/05/2021 (NB. Needs to be DD/MM/YYYY format) - Change all of the rows in the 'voucher_date' column (column L) to the last day of the current accounting period in Agresso. E.g. if the current accounting period is 202105, change this cell to 31/05/2021 (NB. Needs to be DD/MM/YYYY format)
5 | Select 'Add-Ins-Agresso BIF-File-Write' and ensure that a log file is produced. Press 'Yes' when prompted and ensure that the correct number of rows are written to the file. |  | The correct number of rows are written to the file.
6 | Log in to Agresso Desktop. (Client = SB) |  | The user will be able to successfully login into Agresso Desktop.
7 | Navigate to Agresso Financials-Batch Input-Transactions from external system-Batch input transactions from external system
8 | Open the 'UK Upload from Excel (BIF or Postback)' screen. |  | The 'UK Upload from Excel (BIF or Postback)' screen will open.
9 | - Enter the 'Filename' as BH.txt - Enter the 'BatchID' as BH - Leave the 'Period' as the current accounting period in Agresso
10 | Press 'Save(F12)' |  | A report no. will be displayed.
11 | Navigate to Agresso Common. Open the 'Maintenance of ordered reports' screen. |  | The 'Maintenance of ordered reports' screen will open.
12 | Place your cursor on the grey search bar and press 'F7'. |  | The GL07 report will be displayed.
13 | When the report has reached status = 'T' (Terminated), double-click on the GL07 report and open the GL07A_SA and GL07B_SB reports. Check that the transactions on the reports reflect what is shown on the 'Journal' tab of the 'Clash reinstatements journal' BIF template. Make a note of one of the transaction numbers from the GL07B_SB report. |  | The transactions on the reports will reflect what is shown on the 'Journal' tab of the 'Clash reinstatements journal' BIF template.
14 | Navigate to Agresso Financials-General Ledger-Enquiries
15 | Open the 'General ledger transactions' screen |  | The 'Enquiry setup' screen will open.
16 | Enter the transaction number noted in step 13, in the 'From' column in the 'TransNo' row (line 2)
17 | Press 'OK'. Check that the transaction details displayed reflect what is shown on the 'Journal' tab of the 'Clash reinstatements journal' BIF template for that transaction. |  | The transaction number noted in step 13 will be displayed and the details will reflect what is shown on the 'Journal' tab of the 'Clash reinstatements journal' BIF template for that transaction.
General Comments / Notes
Post-Requisites:
Post-Requisite scripts:
Sign-off:
Tested by: |  |  |  | Date:
Signature:
Checked by: |  |  |  | Date:
Signature:

## Report
https://teams.microsoft.com/l/file/0FA099A0-B5E6-4ACE-831E-6C16C9179DBF?tenantId=9a50eba8-7568-447a-bcb9-27a0d464aa80&fileType=xlsx&objectUrl=https%3A%2F%2Fbeazley.sharepoint.com%2Fsites%2FFSS%2FShared%20Documents%2FAgresso%20Upgrade%2FFinance%20testing%20-%20UK%20and%20Ireland%20-%20Reports%2FClash%20reinstatements%20journal.xlsx&baseUrl=https%3A%2F%2Fbeazley.sharepoint.com%2Fsites%2FFSS&serviceName=teams&threadId=19:104f775cb22f4c0a8a625e3659e36b45@thread.tacv2&groupId=ccb060f9-0e88-4acf-a39e-b1c13673006a